# MASTER PURCHASE AGREEMENT - {{PROJECT_NUMBER}} - {{PROJECT_NAME}}

# Document Summary

This Master Purchase Agreement (Agreement) is made and entered into as of {{AGREEMENT_EXECUTION_DATE}}, by and between {{DVELE_PARTNERS_XYZ_LEGAL_NAME}}, a {{DVELE_PARTNERS_XYZ_STATE}} {{DVELE_PARTNERS_XYZ_ENTITY_TYPE}} ('Company'), and {{CLIENT_LEGAL_NAME}}, a {{CLIENT_STATE}} {{CLIENT_ENTITY_TYPE}} ('Client') (collectively the 'Parties').

This section gives Client an overview of what is being signed, what to expect, and what happens at each stage of the project. For full legal terms, refer to the full Agreement.

## What the Client is Signing:

Client is entering into an agreement with Company for the design and purchase of {{TOTAL_UNITS}} high-performance modular home(s). Services may include:

##### Offsite Services: Design, engineering, and manufacturing

##### On-Site Services: Shipping, delivery, installation, and site construction

### Services:

The specific services selected are detailed in Section 1.1. This agreement starts with design only, with subsequent phases requiring Client approval to proceed.

### Initial Payment:

##### Design & Engineering Fee: {{DESIGN_FEE}} - Due upon signing this agreement. Work cannot begin until it's paid.

##### This fee covers all site-specific design, engineering, development coordination, cost estimation, and permitting support needed to provide accurate final pricing, but excludes professional fees, such as Engineer’s Stamping, Site Survey’s, Soil Testing and Geotechnical.

##### Peace of Mind Guarantee: You pay only this fee until Green Light. If final pricing makes the project unfeasible, you can exit gracefully.

### What Happens Next

{{WHAT_HAPPENS_NEXT_TABLE}}

### Important Notes

##### Preliminary estimates at signing are based on initial information. They will be refined during design as site conditions, design decisions, and permitting requirements become clear.

##### At Green Light, manufacturing pricing becomes LOCKED. Site pricing is refined to maximum accuracy but may be subject to change orders if unforeseen conditions arise.

##### You can exit after the design phase (before Green Light) having paid only the Design & Engineering Fee.

##### Optional design work (beyond the base scope) requires Client written approval and additional fees.

### Client's Responsibilities

##### On-Site work: choose to have this included in the contract or hire your own licensed General Contractor to prepare the project site

##### Stay engaged during design.

##### Respond to key decisions on time

##### Make timely payments as per the agreement

### When Does This End?

##### Before Green Light: Either party can terminate. Client pays only for design work completed (the Design & Engineering Fee) and any third party professional fees necessary for the project.

##### After Green Light: Client is fully committed to the locked manufacturing price and refined site estimates. Termination after Green Light may result in significant financial obligations per Section 10.

For questions, reach out to the assigned Company project representative.

### Peace of Mind Guarantee

We understand that designing and building a new home is a major decision. That's why this agreement is structured around clear milestones. At the end of each design milestone, at least until the phase called "Green Light Production Notice," the Client will have the option to continue, pause, or exit the process. Client will only be responsible for work completed up to that point - no hidden commitments, no pressure.

This ensures the Client stays in control throughout the process.

# RECITALS

### Company is engaged in the business of coordinating the design, manufacturing and installation of factory-built homes, also known as modular homes, on Client owned properties.

### Company will engage a third-party modular home manufacturer ("Manufacturer") to fabricate the Home(s) at the Manufacturer's factory facility pursuant to a separate agreement between Company and Manufacturer. Client acknowledges that Manufacturer is not a party to this Agreement, and Client's sole contractual relationship for factory production is with Company.

### If Company-Managed On-Site Services are selected under Recital G below, Company will engage qualified third-party contractors ("On-Site Contractors") to perform site work pursuant to separate agreements between Company and such contractors. Client acknowledges that On-Site Contractors are not parties to this Agreement, and Client's sole contractual relationship for on-site services is with Company.

### Client owns or controls certain real property located at {{DELIVERY_ADDRESS}} (the "Site”) on which Client intends to install one or more modular homes.

### WHEREAS, Client desires to purchase from Company {{TOTAL_UNITS}} modular home unit(s) (individually, a 'Unit' or 'Home'; collectively, the 'Units' or 'Homes'), and Company may provide some or all of the services below:

##### Offsite Services: Design, engineering, manufacturing (factory-related services)

##### On-Site Services: Shipping, logistics, installation, site construction, and related services

##### (The specific scope of Offsite Services and On-Site Services is detailed in Section 1.1); and

### WHEREAS, this Agreement is structured to accommodate single-unit or multi-unit projects, whether for direct-to-consumer clients ('D2C Projects') or business-to-business development partners ('B2B Projects'):

### On-Site Services Provider:

Client must select one of the following options for On-Site Services. This

election determines responsibilities, payment flows, and warranty provisions

throughout this Agreement.

## [IF CLIENT HAS ELECTED 'CLIENT-RETAINED CONTRACTOR (CRC)':]

### OPTION A – CLIENT-RETAINED CONTRACTOR ("CRC")

Client will engage and manage a licensed General Contractor of Client's

choosing to perform all On-Site Services, including but not limited to:

site preparation, foundation work, utility connections, module setting

and installation, and completion work.

Under this option:

##### Client contracts directly with and pays the General Contractor

##### Company retains approval authority over contractor selection

##### Company retains inspection and quality control authority per Exhibit F

##### General Contractor must comply with Company's installation specifications

##### Failure to meet Company standards may void all or part of Limited Warranty

##### On-Site Services costs are NOT included in this Agreement's pricing

[IF CLIENT HAS ELECTED 'COMPANY-MANAGED ON-SITE SERVICES (CMOS)':]

### OPTION B – COMPANY-MANAGED ON-SITE SERVICES ("CMOS")

Company will engage and manage qualified contractors to perform all

On-Site Services under this Agreement.

Under this option:

##### Company contracts with and manages all on-site contractors

##### Client's sole contractual relationship is with Company

##### All On-Site Services costs are included in this Agreement's pricing

##### Company is responsible for on-site work quality and performance

##### Full Limited Warranty coverage applies per Exhibit E

CLIENT'S ELECTION (initial one):

SELECTED OPTION: The {{ON_SITE_SERVICES_SELECTION}} (‘On-Site Service’) has been selected for this Agreement.

{{Client Signature_TABLE}}

### WHEREAS, the total preliminary project cost is {{PRELIMINARY_CONTRACT_PRICE}}, which includes:

##### Design and Engineering: {{DESIGN_FEE}}

##### Offsite Services: {{PRELIMINARY_OFFSITE_PRICE}}

##### If included, On-Site Services: {{PRELIMINARY_ONSITE_PRICE}}

### WHEREAS, the Design & Engineering Fee allows Company to perform site-specific design, engineering and cost estimation. At Green Light Production Notice, Client will receive final pricing. Manufacturing price will be LOCKED at Green Light, while on-site pricing may adjust based on actual site conditions discovered during construction. If final pricing makes the project unfeasible, Client may exit the Agreement per Section 10, having paid only the Design & Engineering Fee;

Peace of Mind Guarantee:

The Design & Engineering Fee allows Company to perform site-specific engineering and cost estimation. During the design process, preliminary estimates will be refined based on actual site conditions, design decisions, and permitting requirements. At Green Light Production Notice, Client will receive final pricing for manufacturing (locked) and refined site cost estimates. If final pricing makes the project unfeasible, Client may exit the Agreement in accordance with Section 10, having paid only for design work completed.

### Final Pricing (Established at Green Light):

##### Off-Site Services price becomes fixed and locked

##### On-Site price estimate, if included, is refined to maximum accuracy

Client must approve final pricing to proceed to production. A detailed pricing breakdown and payment schedule is set forth in Exhibit A (Project Budget) and Exhibit C (Payment Schedule); and

NOW, THEREFORE, in consideration of the foregoing and the mutual covenants and promises set forth herein, and for good and valuable consideration the receipt and sufficiency of which is hereby acknowledged, the Parties, intending to be legally bound, hereby agree as follows:

# ATTACHMENTS

##### Exhibit A. Project Budget

##### Exhibit B. Plans and Specifications Drawing Set and the interior finishes for the Home

##### Exhibit C. Payment Schedule

##### Exhibit D. Design Milestone Schedule

##### Exhibit E. Limited Warranty

##### Exhibit F. Site Responsibility Matrix & Requirements for Warranty Eligibility

##### Exhibit G. State-Specific Provisions

# AGREEMENT

## Section 1. Scope of Services

### Overview

This Agreement covers services selected by Client, which are:

#### Offsite Services (Factory-Related):

##### Design Phase: Develop design, engineering, and permitting necessary to define the modular home(s).

##### Production Phase: Manufacture, assembly, and factory completion of approved modular home(s).

##### Shipping & Logistics: Transportation and delivery of completed modules to the Site.

#### On-Site Services (Non-Factory):

## [IF CLIENT HAS ELECTED 'COMPANY-MANAGED ON-SITE SERVICES (CMOS)':]

##### Installation Services: Craning, setting, and installation supervision of modules.

##### Site Construction Services: Site preparation, foundations, utilities, and completion work.

The Design Phase must be completed before the Production Phase begins. Transition between phases requires written confirmation from both parties (email or signed notice is acceptable). Either party may terminate this Agreement as set forth in Section 10 (Termination), with settlement of amounts due for completed work.

## [IF CLIENT HAS ELECTED 'CLIENT-RETAINED CONTRACTOR (CRC)':]

On-Site Services (Item B above) are not included in this Agreement, Client is responsible to hire a licensed General Contractor, approved by Company, to prepare the site and complete all necessary work before the module(s) arrive at the site (see Exhibit C for details). Any contractor working on the Project must comply with Company's installation requirements to maintain warranty eligibility (see Exhibit F).

### Design Phase

During this phase, Company will:

##### Collaborate with Client to finalize the design and layout.

##### Provide opinion of Probable Cost

##### Incorporate Client's selections from the interior finishes.

##### Prepare one set of stamped structural and MEP (mechanical, electrical and plumbing) drawings to support permitting.

##### Assist with local jurisdiction permitting and planning approvals.

##### Submit to applicable 3rd Party Review Agency

##### Submit plans to applicable state authority for modular approval

##### Provide a detailed cost estimate and estimated production schedule.

##### If applicable, coordinate with Client's General Contractor regarding site requirements and scheduling.

This Design Phase includes:

#### Pre-Design and Feasibility (approx. 1 week):

##### Assess site conditions, utilities, and local permitting requirements to optimize modular design.

#### Market and Program Development (approx. 1 week) :

##### Define project goals, product mix, and features with the Client.

#### Concept and Schematic Design (approx. 2 weeks):

##### Prepare preliminary site plans and layouts in coordination with Client's land planner and or civil engineers.

#### Design Documentation (2-4 months):

##### Produce detailed plans and specifications ready for permitting and factory production.

Company will only begin production after these "Green Light Conditions” below are met:

##### Proof of Client's ownership of the site.

##### Client’s approval of schematic design, interior finishes, and Project Budget.

##### Hiring a licensed General Contractor and submitting their scope and schedule.

##### All necessary permits are issued.

##### Proof of Funds or if Financing a bank letter with direction to pay to Company

##### Payment of the Green Light Production Notice amount.

Once these conditions are satisfied, Company will issue a Green Light Production Notice to begin production including: a delivery schedule and pricing. From this point, the remaining Production Payment Schedule applies.

Before shipment of Client's module(s), if Client hires their own On-Site Contractor, then Client's Contractor must confirm that the foundation and utilities are complete and the site is ready to receive the home. Site readiness is detailed in Exhibit F.

### Timing Dependencies

Client acknowledges that the Milestone Schedule Exhibit D is the agreed upon target schedule and is time sensitive.  Delays in providing any Green Light deliverables, including final design approvals, permit submittals, site readiness documentation, or payment, may impact production and delay the start of manufacturing.

Such delays may also impact pricing and delivery timelines due to production scheduling, supply chain fluctuations, and inflationary costs.

Company will not be liable for delays or cost increases resulting from incomplete or late Green Light deliverables from the Client.

### Production Phase

This phase includes manufacturing the module(s) for Client's project and coordinating delivery. Key points include:

##### Production begins only after mutual written agreement and satisfaction of Green Light Conditions.

##### Company will provide weekly updates on production progress and work in good faith to meet estimated delivery timelines; however delivery dates are not guaranteed and are subject to change.

### On-Site Work and Installation (Refer to Exhibit F)

All On-Site Services shall be performed as specified in Client's election under Recital G: either by Client's retained General Contractor subject to Company approval, or by contractors engaged and managed by Company under this Agreement.

Detailed responsibilities and requirements for the Client and their chosen On-Site contractor are set forth in Exhibit F. Company will hold all On-Site Contractors to the same standards set out in Exhibit irrespective of who Client hires for On-Site Services.

## [IF CLIENT HAS ELECTED 'CLIENT-RETAINED CONTRACTOR (CRC)':]

Client understands and acknowledges that all on-site preparation, foundation work, utility connections, crane staging, and post-delivery finish work are the Client's responsibility or that of Client's General Contractor as described in Exhibit F. If the site is not ready on schedule, delays and additional costs may apply, including storage fees for the module(s).

### Custom Design Services (Optional)

Company offers customizable  Design service that includes but is not limited to:

##### Interior design

##### Furnishings and accessories (artwork, etc.)

##### Staging

Note: Any such optional service selected by the Client will be contracted for in a separate agreement and for an additional charge.

## Section 2. Fees, Purchase Price, and Payment Terms

### Design & Engineering Fee

The Design & Engineering Fee for this project is {{DESIGN_FEE}}, due upon execution of this Agreement. This fee is a condition precedent to the commencement of any work by Company.

The Design & Engineering Fee covers:

##### Site-specific engineering and analysis

##### Architectural, MEP and structural design development (excluding external professional/consultant fees)

##### Cost estimation and budget refinement

##### Permitting support and plan preparation

##### Up to {{DESIGN_REVISION_ROUNDS}} rounds of design revisions

The Design & Engineering Fee EXCLUDES local jurisdiction application fees, local permit fees, professional (engineering, survey, geotechnical) fees  and travel expenses related to local submittals. These fees will be billed separately at actual cost and are due upon receipt of invoice.

Peace of Mind Guarantee: The Design & Engineering Fee is the only payment to Company required until Green Light Production Notice. If Client does not approve final pricing at Green Light, Client may terminate this Agreement per Section 10, having paid only the Design & Engineering Fee for work completed. The Design & Engineering Fee is non-refundable once work begins.

### Custom Design Services Fee (Optional)

Compensation for Custom Design, Permitting, and Site Work Services (Section 1.6) will be billed at an hourly rate. Estimated fees will be provided upon request and updated periodically. Time will be recorded in 15-minute increments, with a minimum billing increment of 30 minutes per activity. Monthly invoices will reflect hours incurred.

###### Optional Design Services will only be performed upon the Client's prior written approval of the scope and estimated hours. No Optional Services will be provided without this pre-approval.

### Reimbursable Expenses

Expenses reasonably incurred by Company for travel, printing, postage, local permit application fees, and local permit fees shall be itemized and reimbursed by the Client at Company's cost plus fifteen (15) percent.

### Total Preliminary Project Cost

TOTAL PRELIMINARY PROJECT COST (At Signing): {{PRELIMINARY_CONTRACT_PRICE}}

This represents the estimated total cost for the complete project, including:

{{PRICING_BREAKDOWN_TABLE}}

Note: The Design & Engineering Fee (Section 2.1) is separate from and in addition to the Total Contract Price.

### Pricing Structure and Refinement Process:

#### AT SIGNING: Client receives preliminary estimates based on initial project information and standard assumptions.

#### DURING DESIGN & ENGINEERING PHASE: Pricing estimates are refined based on:

- Actual site conditions (slopes, soil, utilities, access)

- Final design selections and specifications

- Permitting requirements and jurisdictional standards

- Current material and labor market conditions

#### AT GREEN LIGHT: Client receives final pricing:

    - Offsite Services (Manufacturing): LOCKED and guaranteed subject to respective clauses in Section 5, which are outside of Company's control

    - On-Site Services (Site Work): REFINED estimate (subject to change orders for unforeseen field conditions)

#### CLIENT APPROVAL REQUIRED: Client must approve final pricing to proceed to Production Phase. If Client does not approve, Client may terminate per Section 10.

#### FINAL TOTAL CONTRACT PRICE (At Green Light): {{FINAL_CONTRACT_PRICE}}

###### Any revisions to pricing after Green Light shall be documented via written Change Order signed by both parties.

The prices provided are estimates as of the date this agreement was signed and are subject to change before final designs are completed. Fluctuations may occur due to material selection and design choices affecting overall cost. Additionally, price adjustments may be necessary due to unforeseen changes in supply chain costs, including but not limited to tariffs, commodity price fluctuations, product manufacturer price increases and transportation expenses, which are outside of Company's direct control.

###### Client acknowledges that signing this Agreement secures design services only. The Production Price and On-Site Services costs are subject to adjustment. If any changes are made to the design, spec, or material changes due to permitting details and new information around site specific conditions.

Any revisions to the Total Contract Price shall be documented and acknowledged by the Parties in a revised Project Budget (Exhibit A) or a written Change Order, which shall be incorporated into this Agreement by reference.

### What’s Not Included in This Agreement

To ensure complete transparency, here’s a list of common services and costs not included in this agreement unless expressly stated otherwise:

##### Local permit fees and municipal approvals

##### Specialty equipment such as expansion tanks, secondary fire systems, lift stations or anything not specifically included in Company standard package

##### Furniture, window coverings, or speciality appliance installation

##### Additional Landscaping, driveways, or fencing not specified in the design package

On-Site Services will be completed as per Section 1.1.

### Change Orders

Any increases in costs resulting from Client-requested changes, Client-caused delays or unforeseen site conditions will be added to the Total Contract Price via written Change Order with Client acknowledgment.

Company reserves the right to make certain substitutions of products of like for like.

### Payment Schedule

{{PAYMENT_SCHEDULE_TABLE}}

The detailed, project-specific payment schedule is set forth in Exhibit C and may be adjusted based on the services selected and project structure.

Note: If On-Site Services are selected, those services will be provided by Company.

### Late Payments and Collection

Payments not received when due will accrue interest at 10% per annum or the maximum allowed by law. Company reserves the right to suspend work, delay delivery and pursue legal remedies for non-payment.

### Additional Reimbursable Expenses

Client shall reimburse costs for site visits and reproduction of drawing sets without markup.

## Section 3. Client Responsibilities

The Client plays a critical role in the success of the project. The Client's responsibilities include providing information, coordinating with contractors, and ensuring site readiness as outlined below. Should Client fail to provide timely site access or information, additional fees may apply.

### Project Information and Coordination

Client agrees to:

#### Provide timely and complete information about project goals, design preferences, schedule constraints, space needs, and any special equipment or systems requirements. All required information must be provided prior to commencement of Milestone 1 in Exhibit D - “Milestone Schedule”

#### Supply, within 5 business days, upon Company's written request, all available site information, including:

##### Surveys describing physical characteristics, legal boundaries, easements, and utility locations.

##### Reports from geotechnical engineers, environmental consultants, or other specialists.

##### Results from any required tests, inspections, or feasibility studies.

#### Failure to supply requested information within the required timeframes may result in delays to the schedule and any additional costs will be borne by the Client.

## [IF CLIENT HAS ELECTED 'CLIENT-RETAINED CONTRACTOR (CRC)':]

The Client is responsible for coordinating consultants and contractors, including civil engineers, architects, and permitting consultants, to ensure their work aligns with the services provided by Company.

Client must promptly notify Company in writing of any facts or changes that may impact the design, permitting, site preparation, or installation of the home.

### Access to Site

Client will provide Company and its representatives with reasonable access to the Site as needed to perform services. Client will also ensure that consultants and contractors grant Company access as required throughout the project.

### Legal Authority and Site Control

Before the Client's modules are delivered to the Site, the Client must:

##### Provide proof of ownership or control of the Site sufficient to authorize installation of the home.

##### Maintain legal authority to carry out all required work through final payment.

### General Contractor Engagement

## [IF CLIENT HAS ELECTED 'CLIENT-RETAINED CONTRACTOR (CRC)':]

The Client is responsible for hiring a licensed General Contractor to perform all required on-site work, including site preparation, foundation, utility connections, crane access, and post-delivery finish work as detailed in Exhibit F. Company's scope under this Agreement does not include On-Site Services. Client is solely responsible for contracting with, managing, and paying its General Contractor.

Client must:

##### Enter into a written agreement with a licensed General Contractor for all on-site work in a timely manner.

##### Ensure that the General Contractor meets all requirements in Exhibit F (Contractor Requirements).

##### Ensure that the General Contractor performs all required tasks listed in Exhibit F, including any work that must be completed before delivery.

##### Provide Company with reasonable access to inspect and approve the General Contractor's work.

Company retains authority to inspect and approve (or reject) Client's General Contractor's work. If the General Contractor's work does not meet Company's standards, Company may require corrections before proceeding with delivery or installation. Client is responsible for all costs associated with corrections.

## [IF CLIENT HAS ELECTED 'COMPANY-MANAGED ON-SITE SERVICES (CMOS)':]

Company will engage and manage qualified contractors for all site construction work under this Agreement. Company will coordinate manufacturing delivery schedules with site readiness.

### Green Light Conditions

Client must:

##### Ensure all “Green Light Conditions” described in Section 1.2 are satisfied in a timely manner.

##### Maintain those conditions—such as financing, permit approvals, and site control—through completion of delivery and payment of the Total Contract Price.

If the Client is using financing to pay the Total Contract Price, Client must:

##### Enter into a loan agreement with a lender before this Agreement is signed.

##### Satisfy all lender requirements necessary to fund payments to Company on schedule.

##### Provide letter from the financial institution stating funds are in place for the entire project and will be directed to Company as per the agreed payment schedule in Section 2.8.

## Section 4. Company Responsibilities

### Design and Pre-Production Services as per Section 1.2

The scope of these services may be expanded only upon mutual written agreement pursuant to Section 1.6 (Optional and Custom Design Services).

### Production Services

Upon satisfaction of the Green Light Conditions described in Section 1.2 and issuance of the Green Light Production Notice, Company shall:

##### Commence production of the Home(s) through the Manufacturer at the Manufacturer's facility;

##### Oversee and manage the production process to ensure compliance with the approved design, specifications, and quality standards.

### Delivery and Installation Services

Subject to Client's compliance with site readiness requirements in Exhibit F and timely payments under Section 2, Company shall:

##### Arrange and coordinate transport of the completed modular units to the Site;

##### Coordinate delivery timing with Client's General Contractor (if Client-Retained) or with Company’s on-site contractors (if Company-Arranged Services);

### Insurance

Company shall maintain in full force and effect throughout the term of this Agreement:

##### Workers’ compensation insurance in accordance with applicable state and federal law; and

##### Commercial General Liability Insurance with limits of no less than One Million Dollars ($1,000,000) per occurrence and Two Million Dollars ($2,000,000) in the aggregate.

Certificates of insurance shall be made available to Client upon written request.

## Section 5. Project Schedule and Delays

### Project Timeline

Company shall use commercially reasonable efforts to perform its obligations under this Agreement in accordance with the project schedule provided to Client during the Design Phase (the "Project Schedule"). The Project Schedule is an estimate only and is subject to adjustment based on permitting timelines, factory slot availability, weather, site readiness, material availability, and other contingencies outside of Company’s control. Client acknowledges that time is not of the essence unless otherwise agreed in writing by both parties.

### Preconditions to Commencement of Production

Company shall not be obligated to commence factory production of the Home until all Green Light Conditions, as described in Section 1.2, have been fully satisfied, and both parties have executed the Green Light Production Notice. If such conditions are not met within the anticipated timeline, Company may adjust the Project Schedule accordingly, with notice to Client.

### Site Readiness and Delivery Coordination

## [IF CLIENT HAS ELECTED 'COMPANY-MANAGED ON-SITE SERVICES (CMOS)':]

If Client has elected Company-Managed On-Site Services, such services will be provided by contractors engaged by Company under this Agreement. Company will coordinate manufacturing delivery schedules with site readiness. Client acknowledges that:

##### i.	Company maintains full responsibility for on-site contractors;

##### ii.	Client is not a party to contracts between Company and its contractors;

##### iii.	Company and Company’s Contractors are responsible for on-site work quality and performance;

## [IF CLIENT HAS ELECTED 'CLIENT-RETAINED CONTRACTOR (CRC)':]

Client shall ensure that the Site is ready to receive the Home on or before the scheduled delivery date, including completion of all site work listed in Exhibit F by Client's General Contractor or other contractors. If the Site is not ready as scheduled, Company may, at its sole discretion, (a) delay delivery and charge reasonable storage and handling fees; (b) reallocate delivery logistics and factory output as needed; and/or (c) require a Change Order to reschedule delivery and installation.

### Delay Events

Neither Party shall be liable for any failure or delay in performance due to causes beyond its reasonable control, including but not limited to: acts of God, natural disasters, weather events, strikes or labor disputes, transportation disruptions, acts or omissions of governmental authorities, utility delays, supply chain disruptions, pandemics, or the failure of the other Party or its contractors to perform obligations in a timely manner (“Force Majeure Events”). In the event of a Force Majeure Event, the affected Party shall provide prompt written notice and the Project Schedule shall be equitably extended.

### Change in Timeline

Any material change to the Project Schedule, including a delay caused by Client's change requests, failure to perform obligations, or other acts or omissions, shall be documented through a written Change Order in accordance with Section 2.5. Client acknowledges that changes may result in additional costs and/or delayed delivery and installation timelines. If a change in timeline results in increases to costs to the project, then such increases in costs shall be passed on to Client via written change order.

### Inflation Adjustment Clause:

If production is not initiated within 6 months of Agreement execution for reasons outside of Company’s control, Company reserves the right to adjust the Production Price to reflect market conditions, including inflation, material costs, and labor rates, with documentation provided.

## Section 6. Limited Warranty

###### [STATE-SPECIFIC DISCLOSURE - {{PROJECT_STATE}}]

PURSUANT TO {{PROJECT_STATE_CODE}}, THIS SECTION CHANGES YOUR EXISTING WARRANTY RIGHTS UNDER {{PROJECT_STATE}} LAW, AND REPLACES CERTAIN EXISTING WARRANTIES WITH OUR OWN LIMITED WARRANTY.  PLEASE READ THE ENTIRE SECTION CAREFULLY AND INITIAL AFTER READING ONLY IF YOU AGREE.  YOU HAVE THE RIGHT TO CONSULT WITH AN ATTORNEY BEFORE AGREEING TO WAIVE THESE RIGHTS.

### Exclusive Warranty; Disclaimer of Implied Warranties

Except as expressly set forth in Exhibit E, Company makes no other warranties, express or implied. To the maximum extent permitted by law:

###### All implied warranties, including any warranty of merchantability, fitness for a particular purpose, or habitability, are hereby disclaimed. Client acknowledges that the Limited Warranty provides the exclusive remedy for any defect or failure relating to the Home.

###### If you have read, understand, and agree to this paragraph, please initial here: _____

### Limited Warranty Coverage

Company shall provide Client with a limited warranty for the Home as further described in Exhibit E (Limited Warranty). Subject to the terms and conditions in Exhibit E, Company warrants that:

##### For a period of two (2) years from the date the Home leaves the factory (“Fit and Finish Warranty Period”), the Home shall be free from material defects in materials and workmanship in its interior and exterior finishes;

##### For a period of five (5) years from the date the Home leaves the factory (“Envelope Warranty Period”), the Home’s building envelope (as defined in Exhibit E) shall remain free from water intrusion or structural separation due to defective materials or workmanship;

##### For a period of ten (10) years from the date the Home leaves the factory (“Structural Warranty Period”), the Home shall remain free from material structural defects (as defined in Exhibit E).

###### If you have read, understand, and agree to this paragraph, please initial here: _____

### Other Affirmations Replaced

###### [STATE_DISCLOSURE:{WARRANTY_EXCLUSIVITY}]

!!!!!!!!!!!!This needs to be deleted and added to a state disclosure database that isn’t set up if this paragraph is here!!!!!!!!!! The provisions of paragraphs 6.1 and 6.2 of this section, along with Exhibit E, replace any and all other affirmations or representations of fact contained anywhere else within this document, notwithstanding anything to the contrary set forth in {{PROJECT_STATE_CODE}},Cal. Com. Code § 2316.  The Limited Warranty described in this Section and in Exhibit E is the sole and exclusive warranty available.

###### If you have read, understand, and agree to this paragraph, please initial here: ____

### Pass-Through Manufacturer Warranties

Company shall assign and pass through to Client any warranties provided by manufacturers of appliances, fixtures, and equipment originally supplied with the Home. These third-party manufacturer warranties are the sole and exclusive remedy for any covered defect in such components.

### Exclusion of Consequential and Incidental Damages

To the fullest extent permitted by law, Company shall not be liable for incidental, special, indirect, punitive, or consequential damages, including but not limited to loss of use, lost profits, or cost of temporary housing, arising from any defect in the Home or any breach of this Agreement, regardless of the legal theory asserted.

### Claims Process and Limitation

All warranty claims must be made in writing within the applicable warranty period, and in accordance with the notice and inspection procedures set forth in Exhibit F. No coverage exists for any claim submitted after the expiration of the applicable warranty period.

## Section 7. Intellectual Property, Copyrights, and Licenses; Publicity

### Ownership of Work Product.

Company shall be deemed the sole author and owner of all drawings, plans, specifications, and other deliverables (collectively, the “Work Product”) produced under this Agreement, and shall retain all common law, statutory, and other reserved rights, including copyrights and proprietary interests.

### License to Use Work Product.

Upon execution of this Agreement, Company grants Client a nonexclusive, nontransferable license to use the Work Product solely and exclusively for purposes of constructing, using, maintaining, altering, and adding to the Project, provided Client substantially performs its obligations under this Agreement, including prompt payment of all amounts owed when due. This license permits Client to authorize its contractors, consultants, and vendors to reproduce applicable portions of the Work Product solely and exclusively for performing services related to the Home. The license granted hereunder shall automatically terminate if Company terminates this Agreement pursuant to Section 10.

### Restrictions on Use.

Except as expressly granted herein, no other license or rights shall be implied or granted to Client. Client shall not assign, sublicense, delegate, pledge, or otherwise transfer any license or rights granted without Company's prior written consent. Any unauthorized use of the Work Product shall be at Client's sole risk and without liability to Company or its agents, owners, contractors, or employees.

### Indemnification Regarding Work Product Use.

If Client uses the Work Product without retaining Company, Client releases and agrees to indemnify, defend, and hold harmless Company and its agents, owners, contractors, and employees from all claims, damages, liabilities, losses, costs, and expenses (including attorney fees) arising out of such unauthorized use to the fullest extent permitted by law.

### Publicity Rights.

Client grants Company the unrestricted right to photograph and use images of the Home and Site in advertising and promotional materials solely for Company’s benefit, without any royalty or payment obligations to Client. Company agrees to obtain Client’s prior written consent before publicly disclosing the specific location or address of the Home. Client shall provide reasonable access to the Home and Site for such purposes at mutually agreed times.

## Section 8. Limitation of Liability and Exclusion of Consequential Damages

### Damages

Except as expressly provided, neither party shall be liable to the other for consequential, incidental, punitive, indirect, or special damages, regardless of the legal theory asserted, even if advised of the possibility of such damages.

### Liability

Company’s total liability for claims arising under this Agreement, whether in contract, tort, or otherwise, shall be limited to the total fees paid by Client hereunder. This limitation shall not apply to claims arising from fraud, gross negligence, or willful misconduct by Company, nor to insured claims.

## Section 9. No Obligation to Purchase or Sell; Milestone Review and Approval

### Scope and Milestones.

The Services under this Agreement consist of design, engineering, and production of the Home as described in Section 1. The process shall proceed through defined milestones including but not limited to:

##### Mid Design Price Review

##### Final Design Approval and Green Light Production Notice

##### Fabrication and Assembly

### Milestone Review and Approval.

At the completion of each milestone, Company shall present deliverables and status reports to Client for review. Client shall have a reasonable period (not less than ten (10) business days) to approve, request revisions, or reject the milestone deliverables.

### No Obligation to Purchase or Continue.

Client is under no obligation to purchase the Home or continue to the next milestones of Services unless Client signs off on milestone approval. Similarly, Company is under no obligation to proceed beyond any milestone without Client's written approval and fulfillment of payment or other required conditions.

### Termination or “Out” Option at Each Milestone.

If Client chooses not to approve the milestone deliverables or to continue, Client may terminate this Agreement in accordance with Section 10 by providing written notice within the review period. Company may also terminate or suspend the Agreement at any milestone if Client fails to timely approve, pay, or meet conditions necessary for the next milestone.

### Effect of Termination at Milestone.

If terminated at or before any milestone, Client shall pay for all Services performed and costs incurred by Company up to the effective date of termination, as invoiced and payable within ten (10) days. Upon such termination, Client shall have no rights to any Work Product developed beyond the last approved milestone.

## Section 10. Termination and Milestone Exit Rights

### Termination by Either Party at Milestones.

Either party may terminate this Agreement at the completion of any milestone by providing written notice to the other party within the milestone review period. Termination shall be effective ten (10) days after notice, unless otherwise agreed.

### Termination for Cause or Payment Default.

In addition to milestone termination rights, either party may terminate this Agreement for cause as detailed in Section 12, including Client’s Payment Default or material breach, with applicable cure periods.

### Permitting Delay Exit Clause:

If required permits are not obtained within 4 months of submittal due to circumstances outside Company’s control, Company may terminate this Agreement with 10 days' written notice. In such cases, Client shall pay for services rendered to date, and Company shall retain ownership of all Work Product developed.

### Effect of Termination.

Termination shall not relieve Client of payment obligations for Services performed or costs incurred through the effective date of termination, which shall be invoiced and payable within ten (10) days.

### Termination for Client Convenience.

###### [STATE-SPECIFIC DISCLOSURE - {{PROJECT_STATE}}]

PURSUANT TO {{PROJECT_STATE_CODE}}, THIS SECTION CHANGES YOUR EXISTING WARRANTY RIGHTS UNDER {{PROJECT_STATE}} LAW.  PLEASE READ THE ENTIRE SECTION CAREFULLY AND INITIAL WHERE INDICATED AFTER READING ONLY IF YOU AGREE.  YOU HAVE THE RIGHT TO CONSULT WITH AN ATTORNEY BEFORE AGREEING TO WAIVE THESE RIGHTS UNDER THIS PROVISION.

If Client elects to terminate for convenience at or between milestones, Client shall pay all amounts due for Services rendered and reasonable costs incurred by Company through the termination date. In such cases, Client shall purchase the Home 'as is' (as that term is defined under {{PROJECT_STATE}} law) if production has commenced, and Company's Limited Warranty shall be void to the fullest extent permitted by law, notwithstanding any other clause or paragraph in this document.

###### If you have read, understand, and agree to this paragraph, please initial here: _____

### Suspension of Work.

Company may suspend performance if Client fails to timely approve milestone deliverables, meet conditions, or pay amounts due. If suspension continues for more than thirty (30) days without cure, Company may terminate the Agreement pursuant to Section 12.

## Section 11. Stepped Dispute Resolution

### Mandatory Mediation

In the event of a dispute arising out of or relating to this Agreement or the services to be rendered hereunder, prior to the initiation of any legal proceedings, the Client and Company agree to attempt to resolve such disputes through direct negotiations between the appropriate representatives of each party.  If such negotiations are not fully successful, the parties agree to attempt to resolve any remaining dispute by formal non-binding mediation conducted in accordance with rules and procedures to be agreed upon by the parties.

### Arbitration Demand and Limitations.

All disputes, claims, or breaches arising under this Agreement, including warranty claims, shall be resolved exclusively by arbitration in Delaware, under its Delaware Rapid Arbitration Act (DRAA).

Arbitration must be initiated in writing within six (6) months after the cause of action accrues or the warranty period expires, whichever is shorter, or the claim is barred.

### No Third-Party Joinder.

No third party may be joined in the arbitration without mutual written consent.

### Enforcement and Judgment.

The arbitration award shall be final and binding, and judgment on the award may be entered in any court of competent jurisdiction.

###### If you have read, understand, and agree to paragraphs 11.1 through 11.4, please initial here: ____

## Section 12. Default

### Payment Default.

Client’s failure to pay any amount due under this Agreement when due shall constitute a Payment Default. If Client does not cure the Payment Default within five (5) days of written notice, Company may suspend performance and/or terminate this Agreement.

### Material Breach.

Other material breaches by Client (including failure to meet funding or production conditions) not cured within five (5) days of written notice shall entitle Company to suspend performance and/or terminate this Agreement.

### Rights upon Termination.

Upon termination for default, Company may retain all payments made and pursue all legal and equitable remedies.

## Section 13. Miscellaneous Provisions

### Governing Law and Venue.

This Agreement shall be governed by the laws of the State of {{PROJECT_STATE}}, without regard to conflict of law principles. All disputes shall be brought exclusively in the courts located in {{PROJECT_COUNTY}} County, {{PROJECT_STATE}}, or the U.S. District Court for the {{PROJECT_FEDERAL_DISTRICT}}, to which the parties hereby submit.

### Entire Agreement; Amendments.

This Agreement constitutes the entire understanding between the parties and supersedes prior agreements. Any amendments must be in writing and signed by both parties.

### Assignment.

Neither party may assign this Agreement without prior written consent of the other, except that Company may assign to an affiliate or successor without Client’s consent.

### No Third-Party Beneficiaries.

No third parties shall have any rights under this Agreement.

### Notices.

All notices shall be in writing and deemed effective upon: (i) personal delivery, (ii) two (2) business days after deposit with a national overnight courier, or (iii) verified email receipt, to the addresses set forth above or as updated by written notice.

### Force Majeure.

Neither party shall be liable for delays or failures due to causes beyond reasonable control, including acts of God, war, terrorism, government actions, labor disputes, epidemics, or other unforeseeable events. If such events continue for an extended period making performance impracticable, either party may terminate with ten (10) days’ notice.

### Expanded Force Majeure Coverage

In addition to acts of God, natural disasters, labor strikes, and government actions, the following events shall also be deemed force majeure and relieve Company of performance obligations during their duration:

##### Factory production slot delays or plant closures due to external conditions

##### Module transportation restrictions or unavailability of specialized carriers

##### Permit delays beyond Company’s control caused by municipal backlogs or rule changes

##### Supply chain disruptions that materially affect cost or timeline

Company will notify Client as soon as practicable of any such event and will work in good faith to minimize resulting delays.

### Counterparts; Electronic Signatures.

This Agreement may be executed in counterparts and by electronic transmission, each of which shall be deemed an original.

### State-Specific Provisions

This Agreement is subject to state-specific legal requirements as set forth in Exhibit H (State-Specific Provisions). The provisions of Exhibit H for {{PROJECT_STATE}} are incorporated into this Agreement and control in the event of any conflict with other provisions herein. Company and Client acknowledge that:

##### {{PROJECT_STATE}} law governs this Agreement

##### All work must comply with {{PROJECT_STATE}} building codes ({{BUILDING_CODE_REFERENCE}})

##### Company must comply with {{PROJECT_STATE}} contractor licensing requirements

##### Company must comply with {{PROJECT_STATE}} mechanic's lien law provisions

##### All permits and inspections must comply with {{PROJECT_STATE}} requirements

##### Dispute resolution procedures follow {{PROJECT_STATE}} law

Client acknowledges receipt of Exhibit H and has had the opportunity to review the state-specific provisions applicable to {{PROJECT_STATE}} before executing this Agreement.

IN WITNESS WHEREOF, the parties have executed this Design Services Agreement as of the date first set forth above.

| {{DVELE_PARTNERS_XYZ}} | CLIENT |
| --- | --- |
| By: | By: |
| Name: | {{CLIENT_FULL_NAME}} |
| Title: | {{CLIENT_TITLE}} |

# Exhibit A: Project Budget

Project: {{PROJECT_NAME}} (Project No. {{PROJECT_NUMBER}})

Client: {{CLIENT_LEGAL_NAME}}

Site Address: {{SITE_ADDRESS}}

Total Units: {{TOTAL_UNITS}}

Date: {{EFFECTIVE_DATE}}

## PRICING BREAKDOWN:

### PHASE 1: Design and Engineering

| Item | Description | Amount |
| --- | --- | --- |
| Design & Engineering Fee | Site-specific engineering, design development, cost estimation, and permitting support | {{DESIGN_FEE}} |

### PHASE 2: PRELIMINARY ESTIMATES (Provided at Signing, Refined During Design)

| Item | Description | Amount |
| --- | --- | --- |
| Factory Production | {{HOME_MODEL_1}} | {{HOME_MODEL_1_PRELIMINARY_PRICE}} |
|  | [Add additional units as needed] |  |
| Factory Production | {{HOME_MODEL_X}} | {{HOME_MODEL_X_PRELIMINARY_PRICE}} |
| Preliminary Subtotal | Offsite Services: | {{PRELIMINARY_OFFSITE_PRICE}} |

[IF ON-SITE SERVICES SELECTED:]

### On-Site Services (Site Work) - PRELIMINARY ESTIMATE:

| Item | Description | Amount |
| --- | --- | --- |
| Shipping & Logistics |  | {{SHIPPING_PRELIMINARY_PRICE}} |
| Craning & Installation |  | {{INSTALLATION_PRELIMINARY_PRICE}} |
| Site Preparation & Foundations |  | {{SITE_PREP_PRELIMINARY_PRICE}} |
| Utilities & Connections |  | {{UTILITIES_PRELIMINARY_PRICE}} |
| Completion & Finishing |  | {{COMPLETION_PRELIMINARY_PRICE}} |

Note: Site costs are highly variable based on actual conditions (slopes, retaining walls, soil conditions, utility distances, etc.). These estimates will be refined during the design process as site-specific engineering is completed.

| Item | Description | Amount |
| --- | --- | --- |
| Preliminary Subtotal | On-Site Services: | {{PRELIMINARY_ONSITE_PRICE}} |
| PRELIMINARY TOTAL CONTRACT PRICE | (Design Fee + Preliminary Offsite + Preliminary On-Site) | {{PRELIMINARY_CONTRACT_PRICE}} |

### PHASE 3: FINAL PRICING (Established at Green Light Production Notice)

At Green Light, Client will receive:

- LOCKED Manufacturing Price (Offsite Services) - Fixed and guaranteed

- REFINED Site Cost Estimate (On-Site Services) - Based on completed site engineering

- Final Total Contract Price, subject to unforeseen circumstances with On-Site work, for Client approval

Manufacturing pricing becomes fixed at Green Light. Site pricing is refined to maximum accuracy but may be subject to change orders if unforeseen conditions arise during construction.

Client must approve final pricing to proceed to production. If Client does not approve, Client may exit per Section 10, having paid only the Design & Engineering Fee plus any additional professional fees due.

[FOR MULTI-UNIT PROJECTS:]

### Unit Breakdown:

| Type # | Model | Sq Ft | Bed/Bath | Price |
| --- | --- | --- | --- | --- |
| 1 | {{UNIT_1_MODEL}} | {{UNIT_1_SQFT}} | {{UNIT_1_BEDROOMS}}/{{UNIT_1_BATHROOMS}} | {{UNIT_1_PRICE}} |

### EXCLUSIONS (Not Included Unless Specified):

- Local permit fees and municipal approvals

- Specialty equipment (expansion tanks, secondary fire systems, lift stations)

- Landscaping and hardscaping (unless specified in the Project Scope)

- Off-site improvements or impact fees

- Client-requested upgrades or changes after Green Light

### PRICE ADJUSTMENT PROVISIONS:

Any changes to the Total Contract Price will be added to this Exhibit as an addendum or via written Change Order signed by both parties.

Final pricing for Offsite Services will be confirmed upon design completion and Green Light Production Notice. On-Site Services will be reconciled monthly based on actual costs incurred.

# Exhibit B: Plans and Specifications Drawing Set and interior finishes for the Home

# Exhibit C: Payment Schedule

Project: {{PROJECT_NAME}} (Project No. {{PROJECT_NUMBER}})

Client: {{CLIENT_LEGAL_NAME}}

Total Contract Price: {{CONTRACT_PRICE}}

UNIFIED PAYMENT STRUCTURE (Applies to All Projects - D2C and B2B):

All projects follow the same payment structure:

PHASE 1: DESIGN & ENGINEERING

- Payment: {{DESIGN_FEE}} due at contract signing

- Deliverables: Site-specific engineering, design development, cost estimation, permitting support

- Client receives: Preliminary estimates for manufacturing and site work

PHASE 2: GREEN LIGHT DECISION POINT

- Payment: {{MILESTONE_1_PERCENT}}% of Final Contract Price (due upon Green Light approval)

- Deliverables: Final pricing presented - Manufacturing LOCKED, Site work REFINED

- Client Decision: Approve and proceed to production, OR exit (having paid only Design Fee and any associated Professional Fees)

PHASE 3: PRODUCTION & DELIVERY (If Green Light Approved)

- Payments per milestone schedule in Section 2.9:

- Production Start: {{MILESTONE_2_PERCENT}}%

- Production Completion: {{MILESTONE_3_PERCENT}}%

- Delivery: {{MILESTONE_4_PERCENT}}%

- Installation Complete: {{MILESTONE_5_PERCENT}}%

- Final Payment: Balance retainage

- Retainage Release: {{RETAINAGE_PERCENT}}% after {{RETAINAGE_DAYS}} days

Note: For multi-unit projects, payment milestones may be structured per-unit or per-phase as detailed in the project-specific schedule below.

Note: This payment schedule covers all services provided by Company, including Design & Engineering, Manufacturing (Offsite Services), and On-Site Services. All payments are made to Company.

# Exhibit D: Milestone Schedule

The following Design Milestone Schedule outlines key milestones of the Design Phase, including deliverables, responsibilities, and approval requirements. Dates to be confirmed by the Parties.

| Milestone No. | Description | Deliverable | Target Completion Date |
| --- | --- | --- | --- |
| 1 | Kickoff Meeting | Project brief, goals alignment | [Date] |
| 2 | Preliminary Design Package | Concept floor plans, site layout | [Date] |
| 3 | Design Sign-Off | Final Design Package ready for permitting & production | [Date] |
| 4 | Production | Final cost estimate, production schedule | [Date] |
| 5 | On-site Prep | Ground and / foundations | [Date] |
| 6 | Delivery and Site Finishing | Setting, Stitching and detailed finishing | [Date] |
| 7 | Occupancy | Certificate of Occupancy and transition to warranty period | [Date] |

# Exhibit E: Limited Warranty

[STATE-SPECIFIC DISCLOSURE - {{PROJECT_STATE}}]

PURSUANT TO {{PROJECT_STATE_CODE}}, THIS SECTION (ALONG WITH SECTION 6, ABOVE) CHANGES YOUR EXISTING WARRANTY RIGHTS UNDER CALIFORNIA LAW, AND REPLACES CERTAIN EXISTING WARRANTIES WITH OUR OWN LIMITED WARRANTY.  PLEASE READ THE ENTIRE SECTION CAREFULLY AND INITIAL AFTER READING ONLY IF YOU AGREE.  YOU HAVE THE RIGHT TO CONSULT WITH AN ATTORNEY BEFORE AGREEING TO WAIVE THESE RIGHTS.

If you have read, understand, and agree to Exhibit E, please initial here: _____

### Definitions

“Covered Component” means those specific systems and structural elements described in Sections 3 and 4 below, which were originally supplied by Company or its authorized manufacturers.

“Repair” means correction of the defect by restoring the Covered Component to proper working condition.

“Repair/Replacement” means correction of the defect by providing a comparable component and installing it.

“Term of Coverage” begins on the date the Home leaves Company’s factory and continues according to the applicable coverage period (2-, 5-, or 10-year).

“Failure to Perform Its Intended Function” means the operational or structural failure of a Covered Component due to a defect to the extent that:

- the component no longer functions as designed, or

- continued use would be unsafe or materially impractical

### Warranty Commencement

Warranties begin on the earlier of:

  - Substantial completion of factory delivery and installation on site, or

  - 30 days after factory delivery, unless delays are caused by Company.

This timing ensures protection begins as soon as the modules are delivered and ready for occupancy.

### Warranty Scope

| Warranty Type | Duration | Covered Components |
| --- | --- | --- |
| Fit and Finish | {{DVELE_FIT_FINISH_WARRANTY}} Months | Interior/exterior finishes (e.g., paint, trim, drywall, cabinets, flooring, siding, tile) |
| Building Envelope | {{DVELE_ENVELOPE_WARRANTY}} Months | Roof, exterior walls, foundation system (excluding on-site foundation work not performed by Company) |
| Structural | {{DVELE_STRUCTURAL_WARRANTY}} Months | Structural frame, floor structure, roof structure, load-bearing walls |

### Systems Coverage (2 Years)

Company warrants that the following systems will be free of material defects and operate as intended during the first two (2) years:

- Plumbing System: Supply and drain lines, waste pipes, toilets, faucets, sinks, tubs (excluding hot tubs or spas), water heater.

- Electrical System: Service panel, circuit breakers, interior wiring, outlets, switches, and light fixtures.

- HVAC System: Ductwork, furnace, vents, thermostat, and connections.

### Appliance and Fixture Coverage (Pass-Through)

Company provides no separate warranty for appliances or fixtures (e.g., ranges, refrigerators, dishwashers, lighting fixtures, HVAC units, etc.) but will pass through to Client all applicable manufacturer warranties. Defects in installation by Company are covered under the Fit and Finish warranty for two (2) years.

### Exclusions

This Limited Warranty does not cover:

- Cosmetic issues (e.g., fading, chipping, surface discoloration) not affecting functionality.

- Damage caused by Client, contractors, or others not retained by Company.

- Any defect or issue resulting from improper setup, foundation work, or site conditions not performed or controlled by Company.

- Normal wear and tear or lack of maintenance.

- Modifications, alterations, or repairs performed by others without Company's written approval.

- Water intrusion due to site grading, landscaping, or foundation work not performed by Company.

- Appliances or components subject to manufacturer recalls or third-party warranties.

- Acts of God (e.g., fire, flood, earthquake, windstorm, etc.).

- Rodent, pest, or insect damage.

- Use of the Home for commercial or rental purposes unless expressly approved in writing.

### Claims and Remedies

- Claims must be submitted to Company in writing within thirty (30) days of discovering the defect.

- No coverage is available for claims made after the applicable warranty period expires.

- Client must provide access for Company to inspect and assess the claimed defect.

- Emergency repairs may be authorized by Client only in cases of immediate hazard or safety risk, and only if Company is not reasonably available. Client must retain original parts for inspection.

### Limits of Liability

Company's total liability under this Limited Warranty shall not exceed the Total Contract Price of the Home. Company shall not be liable for any consequential, special, indirect, or incidental damages.

The Remainder Of Page Left Intentionally Blank

# Exhibit F: Site Responsibility Matrix & Requirements for Warranty Eligibility

### COMPANY'S AUTHORITY OVER ON-SITE WORK:

In order for Company to provide the Limited Warranty, regardless of who performs on-site work (Client's GC or Company's contractors), Company must maintain appropriate authority over all contractors, subcontractors, and site activities to protect the integrity of its products and preserve warranty coverage. This authority includes:

- APPROVAL AUTHORITY: Right to approve contractor selection based on qualifications, licensing, insurance, and experience with modular/prefab construction

- PROCESS CONTROL: Authority over all on-site work processes, methods, and sequencing to ensure compliance with Company's installation specifications and quality standards

- TECHNICAL OVERSIGHT: Final authority over all technical details, including foundation specifications, module setting, MEP connections, weatherproofing, and finish work

- INSPECTION RIGHTS: Unrestricted access to the site and all work in progress for quality control inspections at any time

- STOP-WORK AUTHORITY: Right to halt any work that does not meet Company's standards, with contractor obligated to remedy deficiencies before proceeding

- BUDGET OVERSIGHT: Right to review and approve cost estimates and change orders that may affect the quality or integrity of the installation

- FINAL APPROVAL: Authority to conduct final inspection and approve completion before warranty coverage becomes effective

Failure to grant Company these authorities, or failure by contractors to comply with Company's quality standards and installation specifications, may void part or all of the Limited Warranty.

This Exhibit outlines the minimum site and installation requirements that the General Contractor (“GC”) must meet and maintain in order for the Client to be eligible for the Limited Warranty provided by Company, as outlined in this Agreement.

Failure to adhere to these standards may void part or all of the Company warranty.

## [IF CLIENT HAS ELECTED 'CLIENT-RETAINED CONTRACTOR (CRC)':]

Client's agreement with its General Contractor must include provisions granting Company these authorities. Failure to comply with Company's quality standards, installation specifications, or inspection requirements may void part or all of the Limited Warranty.

## [IF CLIENT HAS ELECTED 'COMPANY-MANAGED ON-SITE SERVICES (CMOS)':]

Company maintains full contractual authority over on-site contractors under this Agreement. Company retains technical oversight authority to ensure all on-site work meets quality standards and installation specifications. Failure by contractors to comply with quality standards will be remedied by Company under this Agreement.

Scope of On-Site and Installation Work

## [IF CLIENT HAS ELECTED 'CLIENT-RETAINED CONTRACTOR (CRC)':]

Client shall instruct its General Contractor to perform all work defined below in strict accordance with Company's required quality control processes and warranty requirements. Company retains authority to inspect and approve all on-site work to ensure compliance with Company standards. Client is responsible for all payments to its General Contractor under a separate agreement.

## [IF CLIENT HAS ELECTED 'COMPANY-MANAGED ON-SITE SERVICES (CMOS)':]

Company will engage qualified contractors to perform the On-Site Services under this Agreement. Company will enter into contracts with On-Site contractors. All On-Site services scope, costs, and payment terms are governed by this Agreement. Company retains full authority to ensure all On-Site work meets quality standards and installation specifications.

### RESPONSIBILITY MATRIX:

### Site Preparation and Readiness

Responsible Party: [Client / Company]

The responsible party shall complete all site preparation activities prior to delivery of the modular home(s), including but not limited to:

  - Clearing, grading, excavation, and soil preparation

  - Foundation work, including footings, slab, or crawlspace construction

  - Installation of underground utilities and connections (water, sewer, electric, gas)

  - Ensuring site access and staging areas are established for delivery vehicles and crane operations

  - Compliance with all local zoning, building codes, and permit requirements necessary for site readiness

  - Provision of temporary site facilities such as fencing, sanitation (toilet facilities), and site security

### Delivery Coordination

Responsible Party: [Client / Company]

The responsible party shall coordinate and manage all activities related to the delivery of modular home components, including:

  - Scheduling and facilitating delivery appointments in accordance with Manufacturer’s agreed delivery windows

  - Providing safe and clear access routes for delivery trucks, including turnarounds and staging areas

  - Coordination of crane or heavy equipment for unloading and setting modules onto the foundation

  - Arranging any required traffic control, street closures, or neighbor notifications necessary for delivery

  - Ensuring adequate on-site personnel and equipment are present during delivery to assist with unloading and positioning

### Installation of Modular Home

Responsible Party:  [Client / Company]

The responsible party shall be responsible for all installation activities after delivery, including but not limited to:

  - Setting and securing modular sections onto the foundation according to manufacturer specifications

  - Connecting mechanical, electrical, and plumbing (MEP) systems between modules and site utilities

  - Performing sealing, weatherproofing, and final site connections as needed

  - Coordination with the manufacturer for inspections, punch list items, and warranty walk-throughs

  - Managing any finish carpentry or site-specific work not included in factory construction

### Inspections and Approvals

Responsible Party:[Client / Company]

The responsible party shall schedule, coordinate, and ensure completion of all required inspections and approvals including:

  - Local building department inspections for foundation, framing, MEP, and final occupancy

  - Manufacturer or third-party inspections as required for quality control and warranty compliance

  - Certification of utilities connection and compliance with environmental or safety regulations

### Site Maintenance and Cleanup

Responsible Party: [Client / Company]
The responsible party shall maintain the site in a safe, clean, and orderly condition during and after installation, including:

  - Removal and disposal of all construction debris and packaging materials

  - Site restoration and landscaping as necessary to meet local requirements and project standards

  - Immediate remediation of any damage caused by delivery or installation activities

## [IF CLIENT HAS ELECTED 'CLIENT-RETAINED CONTRACTOR (CRC)':]

Client shall inform its General Contractor (“GC”) and ensure the following is part of their agreement with their chosen Contractor:

### Responsibilities and Indemnification

The Client and Client’s GC assume full responsibility for site safety, compliance, and performance of on-site work.

The Client agrees to indemnify and hold harmless the Manufacturer and its affiliates against claims, damages, or costs arising from site work, delivery, or installation activities performed by the Client or their contractors.

### General Qualifications

The GC must:

- Be a licensed contractor in the jurisdiction of the project.

- Carry general liability insurance and workers’ compensation as required by local law and provide proof to Company prior to site work.

- Have demonstrated experience with modular or prefab installation projects.

### Pre-Installation Site Preparation

GC must follow foundation and anchoring specifications as provided by Company's engineering team.

Site must be:

- Graded and compacted according to local code and Company’s tolerance standards

- Free of standing water or debris

- Accessible by delivery vehicles and cranes (if required)

Utility connections (electrical, water, sewer, gas) must be stubbed and tested according to local code and Company’s location drawings.

### Installation

GC must coordinate with Company on module delivery scheduling, craning, and staging.  Modules must be installed within 72 hours of delivery unless otherwise approved in writing. GC must use assembly and protocols provided by Company, including:

- Sealing, fasteners, and weatherproofing materials

- Exterior finishing where applicable

- System reconnection procedures (HVAC, electrical, plumbing)

Company reserves the right to supervise or audit module setting and initial assembly.

### Post-Installation

The GC must perform the following:

- Blower door test and leak checks (where applicable)

- Complete final finish work as defined in Exhibit [C] (e.g., stairs, trim, site utilities)

- Submit photographic documentation of all major stages if Company personnel are not onsite

GC must correct any site-level issues that could impact the home’s structural integrity, weatherproofing, or indoor air quality.

### Required Documentation

The following must be submitted by the GC to Company for warranty activation:

- Final inspection report or certificate of occupancy

- Completed GC checklist signed by Client and GC

- Photos of all critical installation steps

- Permitting and inspection clearance copies

### Non-Compliance

If Company determines that the GC has not complied with these minimum requirements:

- Company may issue a partial warranty exclusion letter specifying what systems are no longer covered.

Client may be required to engage a Company-recommended installer or correct deficiencies before warranty reactivation.

### Acknowledgment

By proceeding with the Green Light, Client acknowledges this exhibit and agrees to share it in full with their General Contractor.

# Exhibit G - State-Specific Provisions (CA, MT, CO, TX, NV, AZ, WA, NM, UT, ID, OR)

## OVERVIEW

This Exhibit H contains state-specific legal provisions that apply to the project location. {{PROJECT_STATE}} law governs this agreement. Select and include ONLY the provisions for {{PROJECT_STATE}}.

Project State: {{PROJECT_STATE}}

Building Code: {{BUILDING_CODE_REFERENCE}}

Lien Law Jurisdiction: {{LIEN_LAW_STATE}}

## CALIFORNIA (CA)

### CA-1: Contractor Licensing Requirements

All contractors performing work on this project must be properly licensed by the California Department of Consumer Affairs, Contractors State License Board (CSLB).

Licensing Requirements:

- General Contractor: License Type A or B required

- Electrical Contractor: C-10 license required

- Plumbing Contractor: C-36 license required

- HVAC Contractor: C-20 license required

- All contractors must display current license number on contracts and invoices

Company Obligation:

- Verify all contractors have current, active licenses before work begins

- Maintain copies of licenses in project file

- Immediately remove any unlicensed contractor from project

- Client may request proof of licensing at any time

Penalty for Unlicensed Work:

- Work performed by unlicensed contractor is voidable

- Client may refuse to pay for unlicensed work

- Company is responsible for licensing compliance

### CA-2: California Mechanic's Lien Law

Notice to Owner (California Code of Civil Procedure § 8300 et seq.):

NOTICE: By law, those who help to improve your property or supply materials to your property may have legal rights to enforce payment out of the money paid for improvements to the property. This notice is being given to protect those rights.

Preliminary Notice Required:

- All contractors and subcontractors must provide Preliminary Notice within 20 days of first furnishing labor, materials, or equipment

- Preliminary Notice must be in writing and delivered to Client

- Company is responsible for ensuring all parties provide Preliminary Notice

- Failure to provide notice may result in loss of lien rights

Lien Filing Deadline:

- Contractors may file mechanic's lien within 90 days after last furnishing labor or materials

- Client may require Company to obtain lien releases from all contractors before final payment

Lien Release Requirement:

- Before final payment, Company must provide conditional or unconditional lien releases from all contractors and subcontractors

- Company must provide final lien release after receiving final payment from Client

Stop Payment Notice:

- If Company fails to pay contractors, they may serve Stop Payment Notice on Client

- Client may be required to withhold payment to Company to satisfy lien claims

- Company is responsible for managing contractor payments to prevent liens

### CA-3: California Building Code

Applicable Code: 2022 California Building Code (Title 24, Part 2)

Code Compliance:

- All work must comply with 2022 California Building Code

- All work must comply with California Energy Commission Title 24 standards

- All work must comply with local jurisdiction amendments and modifications

- Building permits required for all structural and mechanical work

- Final inspection and approval required before occupancy

Energy Efficiency Requirements:

- All homes must meet Title 24 energy efficiency standards

- Solar-ready provisions required for residential construction

- Cool roof requirements apply to residential roofs

- Water efficiency standards apply to plumbing fixtures

Seismic Requirements:

- Homes in seismic zones must meet seismic design standards

- Cripple wall bracing required where applicable

- Foundation bolting required where applicable

Accessibility Requirements:

- Universal design and visitability standards apply

- Accessible routes and entries required

- Accessible bathrooms and bedrooms required where applicable

### CA-4: Permitting and Inspections

Permit Requirements:

- Building permit required before construction begins

- Electrical permit required for electrical work

- Plumbing permit required for plumbing work

- Mechanical permit required for HVAC work

- Local jurisdiction may require additional permits

Inspection Requirements:

- Rough electrical inspection required

- Rough plumbing inspection required

- Foundation inspection required

- Framing inspection required

- Final inspection required before occupancy

Company Responsibility:

- Company responsible for obtaining all permits

- Company responsible for scheduling all inspections

- Company responsible for correcting any inspection deficiencies

- Company responsible for obtaining final approval

Client Responsibility:

- Client responsible for providing site access for inspections

- Client responsible for obtaining local approval for site work (if Client-Retained Contractor)

- Client responsible for notifying Company of any local requirements

### CA-5: Dispute Resolution - California Law

Governing Law: This agreement is governed by California law, without regard to conflict of law principles.

Venue: Any legal action must be filed in California state courts located in {{PROJECT_STATE}}.

Arbitration (Optional):

- If parties agree, disputes may be resolved through binding arbitration

- Arbitration conducted under JAMS rules

- Arbitrator selected from JAMS panel

- Arbitration held in California

- Costs split equally between parties

Mediation (Preferred):

- Before litigation or arbitration, parties agree to attempt mediation

- Mediator selected by mutual agreement

- Mediation held in California

- Mediation costs split equally

- Mediation must be attempted in good faith

### CA-6: Consumer Protection Provisions

California Consumer Legal Remedies Act (Civil Code § 1750 et seq.):

Company warrants that it will not engage in unfair or deceptive practices in the performance of this agreement.

Unfair Practices Include:

- Misrepresenting the nature, characteristics, or benefits of the work

- Failing to disclose material facts about the work

- Using high-pressure sales tactics

- Making false promises about the work or timeline

- Failing to perform work as promised

Consumer Remedies:

- If Company engages in unfair practices, Client may recover damages

- Client may recover treble damages (3x actual damages)

- Client may recover attorney's fees and costs

- Client may seek injunctive relief

Right to Cancel:

- Client has right to cancel this agreement within 3 business days of signing

- Cancellation must be in writing

- If cancelled within 3 days, Client receives full refund of all payments

- Design Fee is non-refundable only after 3-day cancellation period expires and work begins

### CA-7: Homeowner Protection - Home Improvement Contracts (Civil Code § 7150 et seq.)

Applicable to: Residential construction projects in California

Required Disclosures:

- Company must provide California Home Improvement Contract form

- Contract must include all required disclosures

- Contract must specify scope of work, timeline, and total cost

- Contract must include payment schedule

- Contract must include warranty information

Contractor Information:

- Company must provide license number

- Company must provide workers' compensation insurance information

- Company must provide contact information

- Company must provide notice of cancellation rights

Cancellation Rights:

- Client has 3-day right to cancel home improvement contract

- Cancellation notice must be in writing

- If cancelled: Client receives full refund of deposits

- Design Fee refundable only if work has not begun

Penalty for Non-Compliance:

- Failure to provide required disclosures voids the agreement

- Client may recover damages and attorney's fees

- Company liable for penalties

### CA-8: Workers' Compensation Insurance

Requirement: Company and all contractors must carry workers' compensation insurance.

Coverage Requirement:

- Minimum coverage: Statutory limits

- Coverage must include all employees performing work on project

- Coverage must remain in effect throughout project duration

- Company must provide proof of coverage upon request

Failure to Carry Insurance:

- Client may withhold payment if insurance not provided

- Company liable for all workers' compensation claims

- Client may hire workers' compensation insurance at Company's expense

## COLORADO (CO)

### CO-1: Contractor Licensing Requirements

Licensing Requirement: Colorado does not require state-level licensing for general contractors. However, local jurisdictions may require licensing.

Local Licensing:

- Company must comply with local jurisdiction licensing requirements

- Company must obtain local building contractor license if required

- Company must provide proof of licensing upon request

Specialty Contractor Licensing:

- Electrical contractors must be licensed by Colorado Division of Registrations

- Plumbing contractors must be licensed by Colorado Division of Registrations

- HVAC contractors must be licensed by Colorado Division of Registrations

- Company responsible for verifying specialty contractor licenses

### CO-2: Colorado Mechanic's Lien Law

Notice to Owner (Colorado Revised Statutes § 38-22-101 et seq.):

NOTICE: Persons or companies furnishing labor, materials, or both to improve this property may have lien rights on this property if they are not paid.

Notice Requirement:

- Company must provide Notice to Owner to Client before work begins

- Notice must be in writing

- Company must maintain proof that notice was provided

Lien Filing Deadline:

- Contractors may file mechanic's lien within 4 months after last furnishing labor or materials

- Company must obtain lien releases before final payment

Lien Release:

- Company must provide final lien release after receiving final payment

- Conditional lien releases acceptable during construction

- Unconditional lien release required before final payment

### CO-3: Colorado Building Code

Applicable Code: 2021 International Building Code (IBC) with Colorado amendments

Code Compliance:

- All work must comply with 2021 IBC with Colorado amendments

- All work must comply with local jurisdiction amendments

- Building permits required for all structural work

- Final inspection and approval required

Energy Code: Colorado Energy Code based on 2021 IECC

Electrical Code: National Electrical Code (NEC) current edition

Plumbing Code: International Plumbing Code (IPC) current edition

### CO-4: Permitting and Inspections

Permit Requirements:

- Building permit required

- Electrical permit required

- Plumbing permit required

- Mechanical permit required

Inspection Requirements:

- Foundation inspection

- Framing inspection

- Electrical inspection

- Plumbing inspection

- Final inspection

Company Responsibility:

- Company responsible for obtaining permits

- Company responsible for scheduling inspections

- Company responsible for correcting deficiencies

### CO-5: Dispute Resolution - Colorado Law

Governing Law: Colorado law governs this agreement.

Venue: Any legal action filed in Colorado state courts.

Arbitration: Parties may agree to binding arbitration under Colorado arbitration rules.

Mediation: Parties agree to attempt mediation before litigation.

### CO-6: Prompt Payment Requirements

Payment Timing:

- Company must pay subcontractors and suppliers within 7 days of receiving payment from Client

- Failure to pay timely may result in liability for interest and penalties

- Company responsible for all contractor payment issues

### CO-7: Construction Defect Claims

Notice Requirement:

- If Client discovers defect, Client must provide written notice to Company within 3 years

- Notice must describe defect and location

- Company has opportunity to inspect and repair

Right to Repair:

- Company has right to repair defect before litigation

- Company has 60 days to complete repairs

- If Company refuses or fails to repair, Client may pursue legal action

## TEXAS (TX)

### TX-1: Contractor Licensing

No State Licensing: Texas does not require state-level contractor licensing.

Local Requirements: Local jurisdictions may require licensing; Company must comply with local requirements.

Specialty Licenses:

- Electrical contractors must be licensed by local authority

- Plumbing contractors must be licensed by local authority

- HVAC contractors must be licensed by local authority

### TX-2: Texas Mechanic's Lien Law

Notice to Owner (Texas Property Code § 53.001 et seq.):

NOTICE: If you contract with someone other than a licensed residential contractor, certain provisions of the Property Code do not apply.

Lien Rights:

- Contractors and subcontractors have lien rights if not paid

- Lien must be filed within 4 years after last furnishing labor or materials

- Company must obtain lien releases before final payment

Notice of Non-Payment:

- If Company fails to pay subcontractors, they may notify Client

- Client may be required to withhold payment to Company

### TX-3: ITIN Requirement

Independent Contractor Tax ID (ITIN):

- Company must obtain ITIN from IRS

- Company must provide ITIN to Client upon request

- Company must maintain tax compliance

### TX-4: Texas Building Code

Applicable Code: 2021 International Building Code (IBC) with Texas amendments

Code Compliance:

- All work must comply with 2021 IBC with Texas amendments

- All work must comply with local jurisdiction requirements

- Building permits required

- Final inspection required

Energy Code: Texas Energy Code based on 2021 IECC

### TX-5: Permitting and Inspections

Permits Required:

- Building permit

- Electrical permit

- Plumbing permit

- Mechanical permit

Inspections Required:

- Foundation inspection

- Framing inspection

- Electrical inspection

- Plumbing inspection

- Final inspection

Company Responsibility:

- Company obtains permits

- Company schedules inspections

- Company corrects deficiencies

### TX-6: Dispute Resolution - Texas Law

Governing Law: Texas law governs this agreement.

Venue: Disputes resolved in Texas state courts.

Arbitration: Parties may agree to binding arbitration.

Mediation: Parties agree to attempt mediation before litigation.

### TX-7: Residential Construction Liability

Liability Limitations:

- Company's liability limited to amount paid by Client

- Company not liable for indirect or consequential damages

- Company not liable for delays caused by Client or force majeure

## NEVADA (NV)

### NV-1: Contractor Licensing

Licensing Requirement: Nevada requires state licensing for contractors.

License Types:

- General Contractor: License required from Nevada Contractors Board

- Electrical Contractor: C-2 license required

- Plumbing Contractor: C-1 license required

- HVAC Contractor: C-23 license required

Company Obligation:

- Company must be licensed by Nevada Contractors Board

- Company must provide license number to Client

- Company must maintain current license throughout project

- Company must verify all subcontractor licenses

### NV-2: Nevada Mechanic's Lien Law

Notice to Owner (Nevada Revised Statutes § 108.705 et seq.):

NOTICE: Persons or companies furnishing labor, materials, or equipment may have lien rights against the property.

Lien Filing Deadline:

- Lien must be filed within 90 days after last furnishing labor or materials

- Company must obtain lien releases before final payment

Preliminary Notice:

- Company must provide Preliminary Notice to Client

- Notice must be provided before or with first invoice

- Notice must be in writing

### NV-3: Nevada Building Code

Applicable Code: 2021 International Building Code (IBC) with Nevada amendments

Code Compliance:

- All work must comply with 2021 IBC with Nevada amendments

- All work must comply with local jurisdiction requirements

- Building permits required

- Final inspection required

### NV-4: Permitting and Inspections

Permits Required:

- Building permit

- Electrical permit

- Plumbing permit

- Mechanical permit

Inspections Required:

- Foundation inspection

- Framing inspection

- Electrical inspection

- Plumbing inspection

- Final inspection

Company Responsibility:

- Company obtains permits

- Company schedules inspections

- Company corrects deficiencies

### NV-5: Dispute Resolution - Nevada Law

Governing Law: Nevada law governs this agreement.

Venue: Disputes resolved in Nevada state courts.

Arbitration: Parties may agree to binding arbitration under Nevada rules.

## ARIZONA (AZ)

### AZ-1: Contractor Licensing

Licensing Requirement: Arizona requires state licensing for contractors.

License Types:

- General Contractor: License required from Arizona Registrar of Contractors

- Electrical Contractor: License required

- Plumbing Contractor: License required

- HVAC Contractor: License required

Company Obligation:

- Company must be licensed by Arizona Registrar of Contractors

- Company must provide license number to Client

- Company must maintain current license

- Company must verify all subcontractor licenses

### AZ-2: Arizona Mechanic's Lien Law

Notice to Owner (Arizona Revised Statutes § 34-226 et seq.):

NOTICE: A person who has a lien right may enforce the lien by filing a lien on the property.

Lien Filing Deadline:

- Lien must be filed within 4 months after last furnishing labor or materials

- Company must obtain lien releases before final payment

Notice Requirements:

- Company must provide notice to Client

- Notice must be provided before work begins

- Notice must include Company license number

### AZ-3: Arizona Building Code

Applicable Code: 2021 International Building Code (IBC) with Arizona amendments

Code Compliance:

- All work must comply with 2021 IBC with Arizona amendments

- All work must comply with local jurisdiction requirements

- Building permits required

- Final inspection required

### AZ-4: Permitting and Inspections

Permits Required:

- Building permit

- Electrical permit

- Plumbing permit

- Mechanical permit

Inspections Required:

- Foundation inspection

- Framing inspection

- Electrical inspection

- Plumbing inspection

- Final inspection

Company Responsibility:

- Company obtains permits

- Company schedules inspections

- Company corrects deficiencies

### AZ-5: Dispute Resolution - Arizona Law

Governing Law: Arizona law governs this agreement.

Venue: Disputes resolved in Arizona state courts.

Arbitration: Parties may agree to binding arbitration under Arizona rules.

### AZ-6: Residential Contractor Restrictions

Bonding Requirement:

- Company must maintain surety bond

- Minimum bond amount: {{ONSITE_BOND_AMOUNT}} or as required by Arizona law

- Bond must remain in effect throughout project

Insurance Requirement:

- Company must carry liability insurance

- Minimum coverage: {{ONSITE_LIABILITY_MINIMUM}}

- Company must provide proof of insurance to Client

## WASHINGTON (WA)

### WA-1: Contractor Licensing

Licensing Requirement: Washington requires state licensing for contractors.

License Types:

- General Contractor: License required from Washington Department of Labor & Industries

- Electrical Contractor: License required

- Plumbing Contractor: License required

- HVAC Contractor: License required

Company Obligation:

- Company must be licensed by Washington Department of Labor & Industries

- Company must provide license number to Client

- Company must maintain current license

- Company must verify all subcontractor licenses

### WA-2: Washington Mechanic's Lien Law

Notice to Owner (Washington Revised Code § 60.04 et seq.):

NOTICE: Persons or companies furnishing labor, materials, or equipment may have lien rights against this property.

Lien Filing Deadline:

- Lien must be filed within 90 days after last furnishing labor or materials

- Company must obtain lien releases before final payment

Preliminary Notice:

- Company must provide Preliminary Notice to Client

- Notice must be provided before or with first invoice

- Notice must be in writing

### WA-3: Washington Building Code

Applicable Code: 2021 International Building Code (IBC) with Washington amendments

Code Compliance:

- All work must comply with 2021 IBC with Washington amendments

- All work must comply with local jurisdiction requirements

- Building permits required

- Final inspection required

Energy Code: Washington Energy Code based on 2021 IECC

### WA-4: Permitting and Inspections

Permits Required:

- Building permit

- Electrical permit

- Plumbing permit

- Mechanical permit

Inspections Required:

- Foundation inspection

- Framing inspection

- Electrical inspection

- Plumbing inspection

- Final inspection

Company Responsibility:

- Company obtains permits

- Company schedules inspections

- Company corrects deficiencies

### WA-5: Dispute Resolution - Washington Law

Governing Law: Washington law governs this agreement.

Venue: Disputes resolved in Washington state courts.

Arbitration: Parties may agree to binding arbitration under Washington rules.

### WA-6: Payment and Lien Rights

Prompt Payment:

- Company must pay subcontractors within 10 days of receiving payment from Client

- Failure to pay timely may result in liability for interest and penalties

## NEW MEXICO (NM)

### NM-1: Contractor Licensing

Licensing Requirement: New Mexico does not require state-level contractor licensing. Local jurisdictions may require licensing.

Local Licensing:

- Company must comply with local jurisdiction licensing requirements

- Company must obtain local license if required

- Company must provide proof of licensing upon request

Specialty Contractor Licensing:

- Electrical contractors must be licensed by local authority

- Plumbing contractors must be licensed by local authority

- HVAC contractors must be licensed by local authority

### NM-2: New Mexico Mechanic's Lien Law

Notice to Owner (New Mexico Statutes § 57-3-1 et seq.):

NOTICE: Persons or companies furnishing labor, materials, or equipment may have lien rights against this property.

Lien Filing Deadline:

- Lien must be filed within 6 months after last furnishing labor or materials

- Company must obtain lien releases before final payment

### NM-3: New Mexico Building Code

Applicable Code: 2021 International Building Code (IBC) with New Mexico amendments

Code Compliance:

- All work must comply with 2021 IBC with New Mexico amendments

- All work must comply with local jurisdiction requirements

- Building permits required

- Final inspection required

### NM-4: Permitting and Inspections

Permits Required:

- Building permit

- Electrical permit

- Plumbing permit

- Mechanical permit

Inspections Required:

- Foundation inspection

- Framing inspection

- Electrical inspection

- Plumbing inspection

- Final inspection

Company Responsibility:

- Company obtains permits

- Company schedules inspections

- Company corrects deficiencies

### NM-5: Dispute Resolution - New Mexico Law

Governing Law: New Mexico law governs this agreement.

Venue: Disputes resolved in New Mexico state courts.

Arbitration: Parties may agree to binding arbitration under New Mexico rules.

## UTAH (UT)

### UT-1: Contractor Licensing

Licensing Requirement: Utah requires state licensing for contractors.

License Types:

- General Contractor: License required from Utah Division of Occupational & Professional Licensing

- Electrical Contractor: License required

- Plumbing Contractor: License required

- HVAC Contractor: License required

Company Obligation:

- Company must be licensed by Utah Division of Occupational & Professional Licensing

- Company must provide license number to Client

- Company must maintain current license

- Company must verify all subcontractor licenses

### UT-2: Utah Mechanic's Lien Law

Notice to Owner (Utah Code § 38-1-1 et seq.):

NOTICE: Persons or companies furnishing labor, materials, or equipment may have lien rights against this property.

Lien Filing Deadline:

- Lien must be filed within 90 days after last furnishing labor or materials

- Company must obtain lien releases before final payment

Notice Requirements:

- Company must provide notice to Client

- Notice must be provided before work begins

- Notice must be in writing

### UT-3: Utah Building Code

Applicable Code: 2021 International Building Code (IBC) with Utah amendments

Code Compliance:

- All work must comply with 2021 IBC with Utah amendments

- All work must comply with local jurisdiction requirements

- Building permits required

- Final inspection required

### UT-4: Permitting and Inspections

Permits Required:

- Building permit

- Electrical permit

- Plumbing permit

- Mechanical permit

Inspections Required:

- Foundation inspection

- Framing inspection

- Electrical inspection

- Plumbing inspection

- Final inspection

Company Responsibility:

- Company obtains permits

- Company schedules inspections

- Company corrects deficiencies

### UT-5: Dispute Resolution - Utah Law

Governing Law: Utah law governs this agreement.

Venue: Disputes resolved in Utah state courts.

Arbitration: Parties may agree to binding arbitration under Utah rules.

## IDAHO (ID)

### ID-1: Contractor Licensing

Licensing Requirement: Idaho does not require state-level contractor licensing. Local jurisdictions may require licensing.

Local Licensing:

- Company must comply with local jurisdiction licensing requirements

- Company must obtain local license if required

- Company must provide proof of licensing upon request

Specialty Contractor Licensing:

- Electrical contractors must be licensed by local authority

- Plumbing contractors must be licensed by local authority

- HVAC contractors must be licensed by local authority

### ID-2: Idaho Mechanic's Lien Law

Notice to Owner (Idaho Code § 45-501 et seq.):

NOTICE: Persons or companies furnishing labor, materials, or equipment may have lien rights against this property.

Lien Filing Deadline:

- Lien must be filed within 120 days after last furnishing labor or materials

- Company must obtain lien releases before final payment

### ID-3: Idaho Building Code

Applicable Code: 2021 International Building Code (IBC) with Idaho amendments

Code Compliance:

- All work must comply with 2021 IBC with Idaho amendments

- All work must comply with local jurisdiction requirements

- Building permits required

- Final inspection required

### ID-4: Permitting and Inspections

Permits Required:

- Building permit

- Electrical permit

- Plumbing permit

- Mechanical permit

Inspections Required:

- Foundation inspection

- Framing inspection

- Electrical inspection

- Plumbing inspection

- Final inspection

Company Responsibility:

- Company obtains permits

- Company schedules inspections

- Company corrects deficiencies

### ID-5: Dispute Resolution - Idaho Law

Governing Law: Idaho law governs this agreement.

Venue: Disputes resolved in Idaho state courts.

Arbitration: Parties may agree to binding arbitration under Idaho rules.

## OREGON (OR)

### OR-1: Contractor Licensing

Licensing Requirement: Oregon requires state licensing for contractors.

License Types:

- General Contractor: License required from Oregon Construction Contractors Board

- Electrical Contractor: License required

- Plumbing Contractor: License required

- HVAC Contractor: License required

Company Obligation:

- Company must be licensed by Oregon Construction Contractors Board

- Company must provide license number to Client

- Company must maintain current license

- Company must verify all subcontractor licenses

### OR-2: Oregon Mechanic's Lien Law

Notice to Owner (Oregon Revised Statutes § 87.003 et seq.):

NOTICE: Persons or companies furnishing labor, materials, or equipment may have lien rights against this property.

Lien Filing Deadline:

- Lien must be filed within 90 days after last furnishing labor or materials

- Company must obtain lien releases before final payment

Preliminary Notice:

- Company must provide Preliminary Notice to Client

- Notice must be provided before work begins

- Notice must be in writing

### OR-3: Oregon Building Code

Applicable Code: 2021 International Building Code (IBC) with Oregon amendments

Code Compliance:

- All work must comply with 2021 IBC with Oregon amendments

- All work must comply with local jurisdiction requirements

- Building permits required

- Final inspection required

Energy Code: Oregon Energy Code based on 2021 IECC

### OR-4: Permitting and Inspections

Permits Required:

- Building permit

- Electrical permit

- Plumbing permit

- Mechanical permit

Inspections Required:

- Foundation inspection

- Framing inspection

- Electrical inspection

- Plumbing inspection

- Final inspection

Company Responsibility:

- Company obtains permits

- Company schedules inspections

- Company corrects deficiencies

### OR-5: Dispute Resolution - Oregon Law

Governing Law: Oregon law governs this agreement.

Venue: Disputes resolved in Oregon state courts.

Arbitration: Parties may agree to binding arbitration under Oregon rules.

### OR-6: Construction Defect Claims

Notice Requirement:

- If Client discovers defect, Client must provide written notice to Company within 6 years

- Notice must describe defect and location

- Company has opportunity to inspect and repair

## GENERAL PROVISIONS APPLICABLE TO ALL STATES

### State Selection

This agreement is governed by {{PROJECT_STATE}} law. Only the state-specific provisions for {{PROJECT_STATE}} apply to this project.

If project involves work in multiple states, the primary state is {{PROJECT_STATE}}, and {{PROJECT_STATE}} law governs.

### Building Code Compliance

All work must comply with the current building code adopted by {{PROJECT_STATE}} and local jurisdiction, as referenced in {{BUILDING_CODE_REFERENCE}}.

### Permits and Inspections

Company is responsible for:

- Obtaining all required permits for {{PROJECT_STATE}} and local jurisdiction

- Scheduling all required inspections

- Correcting any inspection deficiencies

- Obtaining final approval before occupancy

### Contractor Licensing

Company and all subcontractors must comply with all licensing requirements for {{PROJECT_STATE}}.

Company must:

- Provide proof of licensing upon request

- Maintain current licenses throughout project

- Verify all subcontractor licenses

- Immediately remove unlicensed contractors from project

### Mechanic's Lien Compliance

Company must comply with mechanic's lien laws for {{PROJECT_STATE}}, including:

- Providing required notices to Client

- Obtaining lien releases before final payment

- Managing contractor payments to prevent liens

- Providing final lien release after project completion

### Dispute Resolution

Disputes arising from this agreement are resolved under {{PROJECT_STATE}} law:

- Governing Law: {{PROJECT_STATE}}

- Venue: {{PROJECT_STATE}} courts

- Arbitration: Available if parties agree

- Mediation: Attempted before litigation

## CLIENT ACKNOWLEDGMENTS

By signing this agreement, Client acknowledges:

☐ Client has reviewed Exhibit H - State-Specific Provisions

☐ Client understands {{PROJECT_STATE}} law governs this agreement

☐ Client understands building code requirements for {{PROJECT_STATE}} ({{BUILDING_CODE_REFERENCE}})

☐ Client understands contractor licensing requirements for {{PROJECT_STATE}}

☐ Client understands mechanic's lien law provisions for {{PROJECT_STATE}}

☐ Client understands permit and inspection requirements for {{PROJECT_STATE}}

☐ Client understands dispute resolution procedures for {{PROJECT_STATE}}

☐ Client understands all applicable consumer protection provisions for {{PROJECT_STATE}}

☐ Client has opportunity to ask questions about state-specific provisions before signing

END OF EXHIBIT H - STATE-SPECIFIC PROVISIONS